## BurndownChart
BURNDOWN CHART - GROUP 041
Daily meeting record | Days | Goal | Done | Goal velocity | Remaining | Hours Spent
| 0 | 0 | 0 | 89 | 89 | 0
| 1 | 2 | 0 | 87 | 89 | 0
| 2 | 4 | 0 | 85 | 89 | 0
| 3 | 6 | 0 | 83 | 89 | 0
| 4 | 8 | 0 | 81 | 89 | 0
| 5 | 10 | 0 | 79 | 89 | 0
| 6 | 12 | 0 | 77 | 89 | 0
| 7 | 14 | 0 | 75 | 89 | 0
Daily 1 (2/12) | 8 | 16 | 0 | 73 | 89 | 0
| 9 | 18 | 0 | 71 | 89 | 6
Daily 2 (4/12) | 10 | 20 | 1 | 69 | 88 | 7
| 11 | 22 | 1 | 67 | 87 | 3
Daily 3 (6/12) | 12 | 24 | 3 | 65 | 84 | 8
| 13 | 26 | 0 | 63 | 84 | 2
| 14 | 28 | 6 | 61 | 78 | 8
Daily 4 (9/12) | 15 | 30 | 4 | 59 | 74 | 4
| 16 | 32 | 1 | 57 | 73 | 6
Daily 5 (11/12) | 17 | 34 | 2 | 55 | 71 | 6
| 18 | 36 | 3 | 53 | 68 | 7
Daily 6 (13/12) | 19 | 38 | 3 | 51 | 65 | 8
| 20 | 40 | 1 | 49 | 64 | 5
| 21 | 42 | -2 | 47 | 66 | 6
Daily 7 (16/12) | 22 | 44 | 6 | 45 | 60 | 6
| 23 | 46 | 0 | 43 | 60 | 6
Daily 8 (18/12) | 24 | 48 | 3 | 41 | 57 | 6
| 25 | 50 | 2 | 39 | 55 | 10
Daily 9 (20/12) | 26 | 52 | 1 | 37 | 54 | 9
| 27 | 54 | 1 | 35 | 53 | 7
Daily 10 (22/12) | 28 | 56 | 4 | 33 | 49 | 7
| 29 | 58 | 1 | 31 | 48 | 0
| 30 | 60 | 0 | 29 | 48 | 0
| 31 | 62 | 0 | 27 | 48 | 0
| 32 | 64 | 0 | 25 | 48 | 7
Daily 11 (27/12) | 33 | 67 | 11 | 22 | 37 | 17
| 34 | 69 | 0 | 20 | 37 | 6
Daily 12 (29/12) | 35 | 72 | 2 | 17 | 35 | 5
| 36 | 74 | 5 | 15 | 30 | 5
| 37 | 77 | 3 | 12 | 27 | 4
| 38 | 79 | 0 | 10 | 27 | 2
Daily 13 (02/01) | 39 | 82 | 3 | 7 | 24 | 8
Daily 14 (03/01) | 40 | 84 | 11 | 5 | 13 | 17
Daily 15 (04/01) | 41 | 87 | 10 | 2 | 3 | 12
| 42 | 89 | 3 | 0 | 0 | 7
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Insert daily meeting record. Can be Yes/no and the link to Git
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update according with the days of the sprint
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Update according with the real done items